## Template
Project: Date:
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
Total Risk Score
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Example
Project: Off Site Date: June 19 20XX
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Management Support | 1. Great Event 2. Super Turnout | Increased motivation | Bill | O | 5 | -5 | -25 | High RSVP | 1. Market 2. Prizes
4 | Catering | Late Food Delivery | Delayed events | Food Services | T | 3.5 | 5 | 17.5 | None | Call 1-Day Prior
3 | Multiple Projects | Lack of capacity | Schedule delays | Bill | T | 4 | 4 | 16 | Missed deadlines | Use Staffing Mgt Plan
2 | Bad Weather | 1. Reduced Turnout 2. Late Start | Reduced impact | Jane | T | 3 | 4 | 12 | Weather Report | Ensure inside venue Plan B
Total Risk Score | [7 empty] | 20.5
May use the Project Risk Score: Total Negative scores - positive scores. Larger the gap--the more risk the project has.
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Risk Exposure
Project Risk Score | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
ABC Project | 60 | 58 | 54 | 58 | 70 | 72 | 67 | 61

## Lab Solution
Project: Office Renovation Project Date: Feb 15, 20XX
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Vendor | Low Commitment Low Quality Work | Schedule Slips Budget Overages | Vendor Manager | Threat | 2 | 5 | 10 | Schedule Slips Defects | Careful Source Selection
2 | Working from Home | Productivity Reduced | Daily Workload Delays | HR | Threat | 2.5 | 3.5 | 8.75 | Missed Deadlines | Working from Home Training
3 | Construction Proximity | Noise Work Disruptions | Lost Productivity | QC | Threat | 3 | 3 | 9 | Worker Complaints | QC Partition Plans
4 | Environmental | Dust and Fibers | Employee Health Suffers | Environmental | Threat | 4 | 4 | 16 | Sick Days | Ensure Proper Filtration
5 | Permits | Delays | Schedule Slips | Electrical | Threat | 1 | 3 | 3 | Permits Delayed | Request Early
6 | Customer Traffic | Enter Construction Area | Injury Risk | HR | Threat | 1 | 5 | 5 | Observation | Directional Signs
7 | Location | Stair Hazard | Safety Incidents | Environmental | Threat | 2 | 4.5 | 9 | Incident Reports | Designated Crew Elevator
8 | Aggressive Schedules | Compressed Milestones | Schedule Slippage | PM | Threat | 4 | 5 | 20 | Milestones Not Met | Ensure Adequate Resources
9 | Team Skill Sets | Experienced Facility Manager | Rapid Issue Resolution | PM | Opportunity | 3 | -3.5 | -10.5 | None | Incentives
10 | Budget | No Constraints | Adequate Resources | Finance | Opportunity | 5 | -5 | -25 | None | Plan Resources Carefully
Total Risk Score | [7 empty] | 45.25
May use the Project Risk Score: Total Negative scores - positive scores. Larger the gap--the more risk the project has.
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low